# Task List - CCHFV Module 4 Online Course

## QC/QA for Molecular Detection

Generated from: PRD_mod4.md
Project: Online PCR Course - Module 4
Owner: Robert ten Hove (RIVM)
Created: October 12, 2025

## 📋 Phase 1: Content Plan

Target Completion: October 20, 2025

### Documentation Tasks

- DOC-001 Prepare downloadable resource library

  - Priority: High

  - Assignee: Production Team

  - Duration: 2 days

  - Dependencies: None

### Content plan

- PLAN-001 Develop course overview and learning objectives

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 3 hours

  - Dependencies: None

- PLAN-002 Create Module 4 content structure and outline

  - Priority: High

  - Assignee: Production Team

  - Duration: 5 hours

  - Dependencies: PLAN-001

- PLAN-003 Write lesson coverview for QC/QA molecular detection

  - Priority: High

  - Assignee: Robert ten Hove + SMEs

  - Duration: 1,5 days

  - Dependencies: PLAN-002

- PLAN-004 Create draft interactive simulations and exercises

  - Priority: Medium

  - Assignee: Robert ten Hove

  - Duration: 0,5 days

  - Dependencies: PLAN-003

## 📋 Phase 2: Content Creation

Target Completion: October 28, 2025

### Content creation

- CONT-001 Introduction

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 0,5 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

- CONT-002 Chapter 1

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 6 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

- CONT-003 Chapter 2

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 6 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

- CONT-004 Chapter 3

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 6 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

- CONT-005 Chapter 4

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 6 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

- CONT-006 Chapter 5

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 6 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

- CONT-007 Summary

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 6 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

### Assessment Development

- ASSESS-001 Design formative knowledge checks

  - Priority: Medium

  - Assignee: Production Team

  - Duration: 6 days

  - Dependencies: PLAN-003

- ASSESS-002 Create summative exam questions

  - Priority: Medium

  - Assignee: Robert ten Hove + SMEs

  - Duration: 8 days

  - Dependencies: CONT-003

- ASSESS-003 Set pass/fail thresholds and scoring criteria

  - Priority: Medium

  - Assignee: Robert ten Hove + SMEs

  - Duration: 2 days

  - Dependencies: ASSESS-002

## 📋 Phase 3: Review

Target Completion: November 07, 2025

### Review & Quality Assurance

- REV-001 SME content review (first round)

  - Priority: High

  - Assignee: External SME + Internal SME

  - Duration: 7 days

  - Dependencies: CONT-003, DOC-001, xxxxxx

- REV-002 Incorporate SME feedback and revisions

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 5 days

  - Dependencies: REV-001

- REV-003 Final SME approval and sign-off

  - Priority: High

  - Assignee: SMEs + Chantal Reusken

  - Duration: 3 days

  - Dependencies: REV-002

# Task List - CCHFV Module 4 Online Course

## QC/QA for Molecular Detection

Generated from: PRD_mod4.md
Project: Online PCR Course - Module 4
Owner: Robert ten Hove (RIVM)
Created: October 12, 2025

## 📋 Phase 1: Content Plan

Target Completion: October 20, 2025

### Documentation Tasks

- DOC-001 Prepare downloadable resource library

  - Priority: High

  - Assignee: Production Team

  - Duration: 2 days

  - Dependencies: None

### Content plan

- PLAN-001 Develop course overview and learning objectives

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 3 hours

  - Dependencies: None

- PLAN-002 Create Module 4 content structure and outline

  - Priority: High

  - Assignee: Production Team

  - Duration: 5 hours

  - Dependencies: PLAN-001

- PLAN-003 Write lesson coverview for QC/QA molecular detection

  - Priority: High

  - Assignee: Robert ten Hove + SMEs

  - Duration: 1,5 days

  - Dependencies: PLAN-002

- PLAN-004 Create draft interactive simulations and exercises

  - Priority: Medium

  - Assignee: Robert ten Hove

  - Duration: 0,5 days

  - Dependencies: PLAN-003

## 📋 Phase 2: Content Creation

Target Completion: October 28, 2025

### Content creation

- CONT-001 Introduction

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 0,5 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

- CONT-002 Chapter 1

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 6 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

- CONT-003 Chapter 2

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 6 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

- CONT-004 Chapter 3

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 6 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

- CONT-005 Chapter 4

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 6 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

- CONT-006 Chapter 5

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 6 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

- CONT-007 Summary

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 6 hours

  - Dependencies: PLAN-001, PLAN-002, PLAN-003

### Assessment Development

- ASSESS-001 Design formative knowledge checks

  - Priority: Medium

  - Assignee: Production Team

  - Duration: 6 days

  - Dependencies: PLAN-003

- ASSESS-002 Create summative exam questions

  - Priority: Medium

  - Assignee: Robert ten Hove + SMEs

  - Duration: 8 days

  - Dependencies: CONT-003

- ASSESS-003 Set pass/fail thresholds and scoring criteria

  - Priority: Medium

  - Assignee: Robert ten Hove + SMEs

  - Duration: 2 days

  - Dependencies: ASSESS-002

## 📋 Phase 3: Review

Target Completion: November 07, 2025

### Review & Quality Assurance

- REV-001 SME content review (first round)

  - Priority: High

  - Assignee: External SME + Internal SME

  - Duration: 7 days

  - Dependencies: CONT-003, DOC-001, xxxxxx

- REV-002 Incorporate SME feedback and revisions

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 5 days

  - Dependencies: REV-001

- REV-003 Final SME approval and sign-off

  - Priority: High

  - Assignee: SMEs + Chantal Reusken

  - Duration: 3 days

  - Dependencies: REV-002

## 🌍 Phase 4: SCORM & Moodle LMS

Target Completion: December 12, 2025

## LMS integration tasks

- SCORM-001 Build SCORM package

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 2 hours

  - Dependencies: REV-003

- SCORM-002 Upload SCORM into Moodle LMS

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 2 hours

  - Dependencies: REV-003

- SCORM-003 Test online course

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 2 hours

  - Dependencies: REV-003

- SCORM-004 Incorporate fixes and revisions

  - Priority: High

  - Assignee: Robert ten Hove

  - Duration: 4 hours

  - Dependencies: REV-001

## 📊 Summary Statistics

- Total Tasks: 84

- High Priority: 45 tasks

- Medium Priority: 35 tasks

- Low Priority: 4 tasks

- Estimated Duration: ~4 months (Sept 2025 - Jan 2026)

- Key Dependencies: SME review, translation completion, pilot feedback

## 🏷️ Task Categories

- Content Development: 22 tasks

- Technical Implementation: 18 tasks

- Translation & Localization: 14 tasks

- Testing & QA: 12 tasks

- Launch & Monitoring: 10 tasks

- Infrastructure & Support: 8 tasks

## ⚠️ Critical Path Items

- SME content review and approval

- Translation completion for target languages

- Moodle platform configuration and testing

- Pilot user feedback incorporation

- Final production deployment

This task list is generated from PRD_mod4.md and should be reviewed and updated regularly as the project progresses.